## Slide 1: AGATA within EURONS
Objectives:
Development, construction, commissioning and evaluation of the first module(s) for an advanced gamma ray tracking array (AGATA) including digital front-end electronics and a data acquisition system capable of handling the gamma-ray tracking procedure
Deliverables:
Full AGATA Prototype system (now planned for 09/08)
(triple-cluster module, local level processing electronics, specific data acquisition hardware,
Evaluation report on full prototype commissioning (12/08) (incl. detector module characterisation, LLP incl. PSA, GLP and tracking, MC simulations and data analysis routines)

## Slide 2: AGATA within the EURONS project - Status and developments in 2008 -
Milestones and deliverables for 2008
  Characterisation of Ge detector prototype (ongoing 06/08)
    Noise problems with detectors/cryostats solved 12/07
    Asymmetric Ge detector delivered to Liverpool 02/08
  Prototype triple-module assembly (ongoing)
    3 cryostat(s) delivered end 2007
    First module completely integrated (111 signals) by 03/08
    Still some minor difficulties to solve before delivery (04/08?)
  Front-end electronics construction (ongoing)
    All final prototypes delivered (04/08)
    Validation test until 05/08; first chain ready by 06/08
    System complete for one triple Ge detector (09/08)
  Data Acquisition system commissioned (ongoing until 05/08)
  AGATA demonstrator subsystems commissioned by 06/08
  Delivery of the full AGATA prototype system by 09/08

## Slide 3: AGATA deliverables for EURONS
D-J08-1.1 | Delivery of the full AGATA prototype system | T-J02-1 | CCLRC | 36 | 45
D-J08-1.2 | Final evaluation report on the full prototype system commissioning | T-J02-1 | CEA-DSM | 48 | 
D-J08-2.1 | Delivery of prototype triple-cluster module | T-J02-2 | U-Köln | 24 | 40
D-J08-2.2 | Report on the characterisation of the detector module | T-J02-2 | U-Liverpool | 48 | 
D-J08-3.1 | Delivery of prototype local level processing electronics | T-J02-3 | IN2P3-IReS | 18 | 18
D-J08-3.2 | Report on local level processing system and pulse shape analysis | T-J02-3 | TUM/IN2P3 | 48 | 
D-J08-4.1 | Delivery of prototypes of specific data acquisition hardware | T-J02-4 | INFN | 18 | 18
D-J08-4.2 | Report on global level processing system and gamma-ray tracking | T-J02-4 | IN2P3/INFN | 48 | 
D-J08-5.1 | Report on MC simulations and data analysis routines | T-J02-5 | U-Uppsala | 48 | 
Reports of all AGATA teams needed by October/November 2008
Please start now to prepare these reports

## Slide 4: EURONS Town Meeting Rhodes, September 17-19, 2008
Venue: Rodos Palace International Convention Center
Abstracts for poster presentations still possible
Registration deadline August 15th, 2008
http://www.gsi.de/informationen/jofu/EURONS/TownMeetingRhodos.html

## Slide 5: AGATA Planning (2008 and beyond)
Demonstrator commissioning at LNL: 2nd semester 2008
First physics campaign at LNL from spring 2009 - ?
  Further campaigns at GANIL (2010/11) and GSI (2011/12)
LoI for construction phase signed in 2005
  First successful bids for new funding (D, I, UK, …)
MoU for AGATA construction and exploitation is ready
  starting in second half 2008, valid until end of 2015
   goal continuous upgrade, 20 AGATA units expected by 2012
ENSAR FP7-I3 Proposal
  support for operation costs (~400k€ for 4 years)
  good evaluation report: 13/15 (threshold 13.5)
  with 4.5/5 for science & implementation 4/5 for management (?)
 reserve list (as in FP6), ongoing lobbying, but chances are slim

## Slide 6: Memorandum of Understanding for construction and exploitation of AGATA
MoU Annexes defining the project
Annexe A.1: List of Parties (i.e. signatories)
Annexe A.2: List of Collaborating Institutions:
  39 laboratories from 10 countries
Annexe B.1: AGATA Equipment and Capital Investment
  Capital costs: 12295 k€ (for 15 new AGATA units)
  Human resources: 200 person-years (in ~4 years)
Annexe B.2: Sharing of Capital investment and Human resources
  3 AGATA units from D,F,I & UK; 2 from S, 1 from Tk,
  Smaller amounts of funding from Ro, Bu, Fin, Pl, …
Annexe B.3: Construction schedule and Milestones
  4 years to complete the 20 unit AGATA system
Annexe B.4: Responsibilities for the construction and operation
  Needs to be worked out over the next 6-12 months
Annexe C.1: AGATA operation costs
Annexe C.2: Sharing of AGATA operation costs
Annexe D: AGATA Management Structure
  ASC, AMB, ACC (representing all collaborating institutions)